## Team
Team Name
Name | Meaning
Kakama | Agile in Te Reo
Team Roles
Name | Team Role | Email | Phone
David Holden | Scrum Master | Dholden.home@gmail.com | 0275275577
Siyoon Jung | Developer | Siyoon9915@gmail.com | 0277774009
Vijay Kumar (VJ) | Product Owner | Saroyav3@gmail.com | 0210331172
Benny Tran | Tester | Bennytran5121@gmail.com | 0224981033

## Vision
Everdose Vision Statement
The problem
Patients who take regular medication may take the wrong type of medication or the wrong dose (over dose, missed dose) because they forget what or when to take it or what has already been taken. They may not be able to distinguish which pills to take and accidently mix or misunderstand prescriptions. Carers, including family members of home patients may not be able to confirm if the right medication has been taken at the right time or be notified of issue in adhering to the prescribed plans.
Vision Statement
FOR patients or carers of patients
WHO need to take or monitor regular medication
THE Everydose Application
IS A Mobile App
THAT helps patients take the right medication, the right dose at the right time by scheduling, recording and confirming doses and notifying patients and carers.
UNLIKE traditional ways of managing medication where pharmacist labels medication and patients remember and track manually

## Backlog
Everdose Product Backlog
# | DESCRIPTION | CATEGRORY | Sprint | STATUS | PRIORITY | POINTS | HOURS | ASSIGNED TO | Acceptance Criteria | COMMENTS
01 | As a patient, | Story - Patient | Sprint 0 | DONE | High | 3 | 16 |  |  | Foundational story to set up basic authentication
I want to be able to register an account with login details
So that only registered authorised users can see or update my medication schedules
02 | As a patient, | Story - Patient | Sprint 0 | DONE | High | 3 | 16 |  |  | High value to the customer. Should be in first release (MVP)
I want to be able to set up a schedule for my prescribed medication
So that I can keep track of all my medications
03 | As a patient, | Story - Patient | Sprint 0 | DONE | High | 3 | 16 |  |  | High value to the customer. Should be in first release (MVP)
I want to be able to view my medication history in the app,
So that I can see whether I've missed any doses.
04 | As a patient, | Story - Patient | Sprint 0 | DONE | High | 3 | 16 |  |  | Reminders should be for all medication as core functionality. High value to the customer. Should be in first release (MVP)
I want to be able to submit an update when my medication is taken
So that I can see my history adherence over time
05 | As a patient, | Story - Patient | Sprint 0 | DONE | High | 3 | 16 |  |  | Reminders should be for all medication as core functionality. High value to the customer. Should be in first release (MVP)
I want to be able to receive reminders for when I need to take medications,
So that I don't forget to take them when I need them.
06 | As a App Owner | Story - Patient | Sprint 1 | DONE | High | 3 | 16 |  | Siyoon | Medium priority as patient features are higher priorty High value for patient wellbeing
I want to make the designs more consistent accross all screens
So that I have a single design standard system
07 | As a patient, | Story - Patient | Sprint 1 | DONE | High | 2 | 4 |  | Benny
I want to be able to edit or delete my schedule,
So that I can keep my schedules up to date to what Ivebeen subscribed.
08 | As an App Owner, | Story - Patient | Sprint 1 | DONE | High | 2 | 4 |  | Siyoon
I want to have terms and conditions accepted by the user before using the app,
So that we are not legally liable if issues in the app cause harm to the patient
09 | As a caregiver, | Story - Caregiver | Sprint 1 | DONE | High | 3 | 16 |  | Vijay
I want to be able to sign up and login and view one or more patient(s) schedule,
So that I can follow up whether the patient takes the right medications and have this information in case of emergencies.
10 | As a caregiver, | Story - Caregiver | Sprint 1 | Ready to Start | High | 2 | 4 |  | Benny | High value to the customer. Should be in first release (MVP)
I want to be able to view my patients medication history in the app,
So that I can see whether I've missed any doses.
11 | As a caregiver, | Story - Caregiver | Sprint 1 | Ready to Start | High | 3 | 16 |  | Siyoon
I want to receive notifications when the patient misses a medication dose,
So that I can remind them to take it.
12 | As a patient, | Story - Caregiver | Sprint 1 | Ready to Start | High | 5 | 24 |  | Vijay | Medium priority as patient features are higher priorty High value for patient wellbeing
I want to be able to grant access to a caregiver,
So that they can provide adequte care
13 | As a caregiver, | Story - Caregiver | Sprint 1 | Ready to Start | High | 3 | 16
I want to be able to view any patient's dose list in the app,
So that I can make sure they're taking the right medication at the right time.
14 | As a caregiver, | Story - Caregiver | Sprint 1 | Ready to Start | High | 2 | 4
I want to be able to view a patient's profile in the app,
So that I can access their contact details, DOB and NHI number
15 | As a caregiver, | Story - Caregiver | Sprint 1 | Ready to Start | Medium | 2 | 4
I want to be able to edit or delete my patients schedule,
So that I can keep their schedules up to date to what they have been subscribed.
16 | As a caregiver responsible for multiple patients, | Story - Caregiver | Sprint 1 | On Hold | Low | 5 | 24 |  |  | Medium priority as patient features are higher priorty High value for patient wellbeing
I want to be able to view medication schedules for multiple patients within the app,
So that I can efficiently monitor and provide care for each patient.
17 | As a patient or caregiver, | Story - Caregiver | Sprint 1 | On Hold | Low | 0 | 0
I want the Everydose Application to integrate with emergency contacts,
So that I can easily reach out for help in case of a medication-related emergency.
18 | As a patient, | Story - Patient | Sprint 1 | On Hold | Low | 0 | 0
I want to be able to take a picture of my medications before intake,
So that a carer could investigate my record if any medical issue happened.
19 | As a patient, | Story - Patient |  | On Hold | Low | 0 | 0
I want to be able to communicate with caregiver or in-charged nurse through the app in real-time,
So that I can ask for help or if I have any enquiries about the medication.
20 | As a patient, | Story - Patient |  | On Hold | Low | 0 | 0 | Name
I want to be able to schedule my medication times in the app,
So that I can receive reminders when it's time to take my medication
21 | As a patient, | Story - Patient |  | On Hold | Low | 0 | 0 |  |  | Low value as patient can see how much medication they have left when they take a dose
I want to be able to receive reminders when I need to refill my medication,
So that I don't run out.
22 | As a patient, | Story - Patient |  | On Hold | Low | 0 | 0 |  |  | Low value for the patient.
I want the app to display relevant information about each medication, such as side effects, interactions, and precautions.
So that I can understand the medications better and avoid potential mix-ups or misunderstandings.
23 | As a patient , | Story - Patient |  | On Hold | Low | 0 | 0 |  |  | Not a common use case for patients Caregivers wouldnt be able to see changes.
I want to be able to access my medication schedule and information offline,
So that I can continue managing my medications even without internet access.
24 | As a caregiver, | Story - Caregiver |  | On Hold | Low | 0 | 0 |  |  | Not as high value to patient wellfare as when patient misses a dose
I want to receive notifications when the patient takes a medication dose,
So that I can keep updating their intake.
25 | As a caregiver, | Story - Caregiver |  | On Hold | Low | 0 | 0
I want to be able to view the patient's medication intake photos taken,
So that I can make sure whether the patient takes the right medications.
26 | As a caregiver, | Story - Caregiver |  | On Hold | Low | 0 | 0 |  |  | This is doctors job not target user
I want to be able to track the patient's medication adherence over time,
So that I can see if there are any patterns or issues that need to be addressed.
BACKLOG
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
XX
X
XX
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Sticky Note
Sticky Note
Sticky Note
Sticky Note

## AC's
Everdose Product Acceptance Criteria
# | DESCRIPTION | PRIORITY | Assigned to | Acceptance Criteria
01 | As a patient, | High |  | • Patient/Carer can register in the app and login successfully • An unregistered user cannot login and use the app • The app displays relevant error message for unregistered users • User can change password or reste password (forgot [assword)
I want to be able to register an account with login details
So that only registered authorised users can see or update my medication schedules
02 | As a patient, | High |  | • Patient is able to add a schedule of medications prescribed including time, day, dose and frequency • The app displays a list of medications prescribed to patient • Patient is able to update schedule of medications prescribed and the apps updates the list and saves • Patient is able to delete schedule of medications prescribed and the apps updates and saves • All data from schedules are stored in medication schedule database.
I want to be able to set up a schedule for my prescribed medication
So that I can keep track of all my medications
03 | As a patient, | High |  | • The app displays medication name, dosage and schedule and which has been taken and which are pending. • The app displays date and time scheduled in each history. •The app should display and highlight missed doses. • The patient can mark a specific history as taken and the app updates the list and saves. • Any changes from history are stored in medication schedule database.
I want to be able to view my medication history in the app,
So that I can see whether I've missed any doses.
04 | As a patient, | High |  | • The patient can mark a dose as taken and the app updates the list and saves. • Any changes from history are stored in medication schedule database.
I want to be able to submit an update when my medication is taken
So that I can see my history adherence over time
05 | As a patient, | High |  | • The app display a reminder on patient's phone, 15 minutes prior to the medication is due. • The reminder display times (morning, afternoon, dinner or bedtime medication) of the medication due . • The reminder lists all the medication due for that specific time.
I want to be able to receive reminders for when I need to take medications,
So that I don't forget to take them when I need them.
06 | As a App Owner | High | Siyoon | • The app should have unified design • The app navigation should follow three click rule • The app should not have many information in one page for readability • All functions should be straight forward and understandable
I want to make the designs more consistent accross all screens
So that I have a single design standard system
07 | As a patient, | High | Benny | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) • Patient is able to select and edit the details (medication name, dosage, time, day, frequency) of an existing schedule in the app. • The edited details are saved in the medication schedule database. • The app displays an updated schedule list, reflecting the changes made by the patient. • Patient is able to select and delete an existing schedule in the app. • The deleted schedule is removed from the medication schedule database. • The app displays an updated schedule list, excluding the deleted schedule.
I want to be able to edit or delete my schedule,
So that I can keep my schedules up to date to what Ivebeen subscribed.
08 | As an App Owner, | High | Siyoon | • The register page shows the app's terms and conditions to be read and checked • The user cannot register without terms and conditions' acceptance • The user should be able to view the whole terms and conditions document • The caregiver received the correct cargiver T&Cs and not the and patient T&Cs • The patient received the correct T&Cs and not the caregivers T&Cs
I want to have terms and conditions accepted by the user before using the app,
So that we are not legally liable if issues in the app cause harm to the patient
09 | As a caregiver, | High | Vijay | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) '• The app should validate the user's credentials (username and password) against the stored data. • The app should check if account exist or not, appropriate message displayed for account doesn't exist. • Appropriate error messages should be displayed for invalid login attempts (e.g., incorrect username or password). • Clear instructions or hints should be provided to users if their login fails. • Once logges in, list of patients is displayed sorted by the whom the medication is due next. • Each patient's schedule should show relevant details such as schedule times, dates, and any other necessary information. • If no patients are assigned to my account, a message should be displayed indicating that there are no schedules to view.
I want to be able to sign up and login and view one or more patient(s) schedule,
So that I can follow up whether the patient takes the right medications and have this information in case of emergencies.
10 | As a caregiver, | High | Benny | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) '• Caregiver is able to view patient's medication history in the app, upon authorization. • The app displays medication name, dosage, and schedule, indicating whether the dose has been taken or is pending for each patient. • The app displays date and time scheduled in each patient's history. • The app should highlight missed doses in the patient's history. • Caregiver can't edit or delete the medication history. They can only view it.
I want to be able to view my patients medication history in the app,
So that I can see whether I've missed any doses.
11 | As a caregiver, | High | Siyoon | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) '• The app should check whether a patient took a scheduled dose or not • The app notifies a caregiver about the missed doses after 60 mins • the app can only send notification to the caregivers who are in charge of the patient • the notification shows who missed dose, when scheduled, details of dosage • the app should support both online and offline notification • online notification should be app notification on a screen • offline notification should be text message
I want to receive notifications when the patient misses a medication dose,
So that I can remind them to take it.
12 | As a patient, I want to be able to grant access to a caretaker, | High | Vijay | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) • Patient can access a settings or profile page where he can manage access permissions. • On the settings or profile page, there should be an option to grant access to a caretaker. • When selecting the option to grant access, patient should be able to provide the caretaker's email address or username. • After entering the caretaker's email address or username, the system should send an invitation to the caretaker. • The invitation should include a clear message explaining that I, as the patient, he/she granting access to their health information and schedules. • When the caretaker receives the invitation, they should be able to click on the provided link to accept it. • Once the caretaker accepts the invitation, they should be granted access to the patient's schedule and relevant health information. • The patient should have the ability to manage and revoke access permissions for caretakers at any time. • If the patient revoke access the caretakers can no longer access patients data.
I want to be able to grant access to a caretaker,
So that they can provide adequte care
13 | As a caregiver, | High | David | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) • Caregiver is able to view the correct dose plan for any selected patient • The dose plan displays the correct medication name, dosage, interval and method for the selected patient. • The dose plan displays all the medications assigned to the patients schedule. No additional medicatoins are displayed. • Caregiver can't edit or delete the dose list. They can only view it.
I want to be able to view any patient's dose list in the app,
So that I can make sure they're taking the right medication at the right time.
14 | As a caregiver, | High | David | • The app design must comply with the design system elements (fonts, buttons lists, page layouts, messages etc) • Caregiver is able to view the correct profile for any selected patient • The profile displays the correct patients name, mobile no, email address, DOB and NHI Number • Caregiver can't edit or delete the profile. They can only view it.
I want to be able to view a patient's profile in the app,
So that I can access their contact details, DOB and NHI number
15 | As a caregiver, | Medium
I want to be able to edit or delete my patients schedule,
So that I can keep their schedules up to date to what they have been subscribed.
16 | As a caregiver responsible for multiple patients, | Low
I want to be able to view medication schedules for multiple patients within the app,
So that I can efficiently monitor and provide care for each patient.
17 | As a patient or caregiver, | Low
I want the Everydose Application to integrate with emergency contacts,
So that I can easily reach out for help in case of a medication-related emergency.
18 | As a patient, | Low
I want to be able to take a picture of my medications before intake,
So that a carer could investigate my record if any medical issue happened.
19 | As a patient, | Low
I want to be able to communicate with caregiver or in-charged nurse through the app in real-time,
So that I can ask for help or if I have any enquiries about the medication.
20 | As a patient, | Low
I want to be able to schedule my medication times in the app,
So that I can receive reminders when it's time to take my medication
21 | As a patient, | Low
I want to be able to receive reminders when I need to refill my medication,
So that I don't run out.
22 | As a patient, | Low
I want the app to display relevant information about each medication, such as side effects, interactions, and precautions.
So that I can understand the medications better and avoid potential mix-ups or misunderstandings.
23 | As a patient , | Low
I want to be able to access my medication schedule and information offline,
So that I can continue managing my medications even without internet access.
24 | As a caregiver, | Low
I want to receive notifications when the patient takes a medication dose,
So that I can keep updating their intake.
25 | As a caregiver, | Low
I want to be able to view the patient's medication intake photos taken,
So that I can make sure whether the patient takes the right medications.
26 | As a caregiver, | Low
I want to be able to track the patient's medication adherence over time,
So that I can see if there are any patterns or issues that need to be addressed.

## S1 Tasks
Sprint 1 Backlog Tasks
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Test Cases
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
DH
BT
DH
SJ
VK
SJ
VK
SJ
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from user testing and test cases results
BT
DH
BT
DH
BT
DH
SJ
VK
SJ
VK
SJ
VK
BT
DH
BT
DH
BT
DH
SJ
VK
SJ
VK
SJ
VK
US13 - Wireframes
As a patient I want to be able to view the patient's (dose list in the app
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,

## S1 Planning
Sprint 1 Planning
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from testing results
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
SJ
DH
SJ
VK
BT
DH
SJ
VK
VK
VK
BT
BT
SJ
SJ
BT
BT
US13 - Wireframes
As a patient I want to be able to view the patient's (dose list in the app
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
DH
VK
VK
BT
BT
BT
DH
DH
DH
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,
DH
VK
VK

## S1 Day 2
Sprint 1 Day 2
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from testing results
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
SJ
DH
SJ
VK
BT
DH
SJ
VK
VK
VK
BT
BT
SJ
SJ
BT
BT
US13 - Wireframes
As a caregiver I want to be able to view any patient's dose plan in the app.
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
DH
VK
VK
BT
BT
BT
DH
DH
DH
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,
DH
VK
VK

## S1 Day 4
Sprint 1 Day 4
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from testing results
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
SJ
DH
SJ
VK
BT
DH
SJ
VK
VK
VK
BT
BT
SJ
SJ
BT
BT
US13 - Wireframes
As a caregiver I want to be able to view any patient's dose plan in the app.
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
DH
VK
VK
BT
BT
BT
DH
DH
DH
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,
DH
VK
VK

## S1 Day 5
Sprint 1 Day 5
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from testing results
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
SJ
DH
SJ
VK
BT
DH
SJ
VK
VK
VK
BT
BT
SJ
SJ
BT
BT
US13 - Wireframes
As a caregiver I want to be able to view any patient's dose plan in the app.
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
DH
VK
VK
BT
BT
BT
DH
DH
DH
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,
DH
VK
VK

## S1 Day 6
Sprint 1 Day 6
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from testing results
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
DH
SJ
VK
BT
DH
SJ
VK
VK
VK
BT
BT
BT
BT
US13 - Wireframes
As a caregiver I want to be able to view any patient's dose plan in the app.
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
DH
VK
VK
BT
BT
BT
DH
DH
DH
SJ
SJ
SJ
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,
DH
VK
VK

## S1 Day 8
Sprint 1 Day 8
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
User Testing of customer journeys
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
Create clickable wireframes
Pattient and caregiver customer journeys
Update designs from testing results
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
DH
SJ
VK
BT
DH
SJ
VK
VK
VK
BT
BT
BT
BT
US13 - Wireframes
As a caregiver I want to be able to view any patient's dose plan in the app.
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
VK
VK
BT
BT
BT
DH
DH
DH
SJ
SJ
SJ
DH
Create new designs for Submit Intake in design system
Create design for Caregiver bottom Nav bar
DH
DH
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
US14 - Run Tests
I want to be able to view a patient's profile in the app,
DH
VK
VK

## S1 Day 10
Sprint 1 Day 10
Sprint Goal: Create a working product for caregivers and enhance existing patients care. Complete customer journeys and designs and test cases for top priority caregiver user stories.
TEAM | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
US07 - Wireframes
As a patient, I want to be able to edit or delete my schedule
US07 - Test Cases
As a patient, I want to be able to edit or delete my schedule
US07 - Run Tests
As a patient, I want to be able to edit or delete my schedule
US08 - Wireframes
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Test Cases
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US08 - Run Tests
As an App Owner I want to have terms and conditions accepted by the user before using the app,
US09 - Wireframes
As a caregiver, I want to be able to sign up, login and view 1 or more patient(s) schedules
US09 - Test Cases
As a caregiver,I want to be able to sign up and login and view 1 or more patient(s) schedules
US09 - Run Tests
As a caregiver, I want to be able to sign up and login and view 1 or more patient(s) schedules
US10 - Wireframes
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Test Cases
As a caregiver, I want to be able to view my patients medication history in the app
US10 - Run Tests
As a caregiver I want to be able to view my patients medication history in the app
US11 - Wireframes
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Test Cases
As a caregiver, I want to receive notifications when the patient misses a medication dose
US11 - Run Tests
As a caregiver, I want to receive notifications when the patient misses a medication dose
US12 - Wireframes
As a patient, I want to be able to grant access to a caretaker
US12 - Test Cases
As a patient, I want to be able to grant access to a caretaker
US12 - Run Tests
As a patient, I want to be able to grant access to a caretaker
US06 - Wireframes
As an App Owner I want to make the designs more consistent
US06 - Test Cases
As an App Owner I want to make the designs more consistent
BT
DH
BT
BT
DH
SJ
VK
VK
US06 - Run Tests
As an App Owner I want to make the designs more consistent
BT
BT
BT
DH
SJ
VK
SJ
VK
BT
BT
DH
SJ
VK
SJ
VK
VK
SJ
DH
VK
VK
BT
BT
BT
BT
US13 - Wireframes
As a caregiver I want to be able to view any patient's dose plan in the app.
US13 - Test Cases
As a patient, I want to be able to view the patient's medication (dose list) in the app
US13 - Run Tests
As a patient, I want to be able to view the patient's medication (dose list) list and dosages in the app
VK
VK
BT
BT
BT
DH
DH
DH
SJ
SJ
SJ
DH
US14 - Wireframes
I want to be able to view a patient's profile in the app
US14 - Test Cases
I want to be able to view a patient's profile in the app,
DH
VK
US14 - Run Tests
I want to be able to view a patient's profile in the app,
VK
Create new designs for Submit Intake in design system
Create design for Caregiver bottom Nav bar
DH
DH
Update designs from testing results
BT
DH
SJ
VK
User Testing of customer journeys
Create clickable wireframes
Pattient and caregiver customer journeys
SJ
VK

## S1 Test Cycle 1
SPRINT 1 TEST CASES
US06 - I want to make the designs more consistent accross all screens - Vijay
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
6 | 1 | App Design - Color consistency. | Verify that the color palette used is consistent across screens. | The color palette used across all screens is consistent, with primary, secondary, and accent colors applied uniformly. | Same as expected Results | Pass
| 2 | App Design - Color consistency. | Check for any color variations or deviations that might impact design consistency | There are no color variations or deviations that impact design consistency. | Same as expected Results | Pass
| 3 | App Design - Typography consistency. | Check for any variations in headings, body text, and other typographic elements. | Font styles (typeface, size, weight) are consistent throughout the application. Headings, body text, and other typographic elements adhere to the defined style guide | Same as expected Results | Pass
| 4 | App Design - Typography consistency. | Ensure that typography follows the defined style guide and enhances readability. | Adhere to the defined style guide, enhancing readability and maintaining consistency. | Same as expected Results | Pass
| 5 | App Design - Alignment spacing consistency | Verify that alignment (horizontal and vertical) is consistent across screens. | UI elements on each screen exhibit consistent alignment, both horizontally and vertically | Same as expected Results | Pass
| 6 | App Design - Alignment spacing consistency | Check if spacing between elements (margins, padding) is consistent and visually balanced. | Spacing between elements (margins, padding) is visually balanced and consistently applied. The layout adheres to grids and guidelines defined in the design system. | Same as expected Results | Pass
| 7 | App Design -iconography consistency | Review the use of icons on different screens. | The same set of icons is consistently used across different screens of the application. | Same as expected Results | Pass
| 8 | App Design -iconography consistency | Verify that the same set of icons is consistently used throughout the application. | The same set of icons is consistently used across different screens of the application. | Same as expected Results | Pass
| 9 | App Design -iconography consistency | Check for any variations in icon styles, sizes, or shapes. |  | Same as expected Results | Pass
| 10 |  |  | Icon styles, sizes, and shapes remain consistent | Same as expected Results | Pass
| 11 | App Design -iconography consistency | Ensure that icons are aligned with the overall visual language and design principles. | Aligning with the overall visual language and design principles. | Same as expected Results | Pass
[5 empty] | Same as expected Results | Pass
| 12 | App Design - button and form element consistency | Check if form elements (input fields, buttons) have a consistent appearance. | Form elements, including input fields, checkboxes, and buttons, maintain a consistent appearance. | Same as expected Results | Pass
| 13 | App Design - button and form element consistency | Verify that button styles (size, shape, color) are consistent across screens. | Button styles (size, shape, color) are consistent across screens, providing a cohesive look and feel. | Same as expected Results | Pass
| 14 | App Design - button and form element consistency | Navigate to screens that contain buttons and form elements. | Interactions such as focus behave consistently for buttons and form elements. | Same as expected Results | Pass
| 15 | App Design - Error and feedback messages consistency: | Verify that error messages and feedback notifications are consistent. | Error messages and feedback notifications maintain consistency in terms of color, typography, and placement. | Same as expected Results | Pass
| 16 | App Design - Error and feedback messages consistency: | Check for any variations in color, typography, or placement of error messages. | consistency in terms of color, typography, and placement. | Same as expected Results | Pass
| 17 | App Design - Error and feedback messages consistency: | Ensure that error messages provide clear and actionable information. | Provides clear and actionable information consistently across screens, ensuring a seamless user experience. | Same as expected Results | Pass
| 18 | App Design - validate navigation consistency. | Navigate through different screens using the application's navigation. | There are no variations in navigation styles, placement, or interaction patterns. | Same as expected Results | Pass
| 19 | App Design - validate navigation consistency. | Verify that the navigation elements are consistent. | The navigation elements are consistent across screens. | Same as expected Results | Pass
| 20 | App Design - validate navigation consistency. | Check for any variations in navigation styles, placement, | There are no variations in navigation styles, placement, or interaction patterns. | Same as expected Results | Pass
| 21 | App Design - validate navigation consistency. | Ensure that users can easily navigate between screens without confusion. | Users can easily navigate between screens without confusion. | Same as expected Results | Pass
US07 - As a Patient, I want to be able to edit or delete my schedule - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
7 | 1 | Edit Schedule | Patient tap on a schedule in schedule list to edit or delete | The edit schedule page displayed with all information about the chosen schedule | The edit schedule page displayed with all information about the chosen schedule | PASS
| 2 | Edit Schedule | Patient selects and edit medication name, dosage, time,... then saves | User sees updated medication name, time, day, frequency in the schedule list | User sees updated medication name, time, day, frequency in the schedule list | PASS
| 3 | Edit schedule | Schedule edit fails when the user tries to save without providing the medication name | Show an error message stating that the medication name is required | No error message showing that the medication name is required | FAIL
| 4 | Edit schedule | Schedule edit fails when user tries to save with invalid day (day in the past) | Show an error message stating that the day is invalid | No error message showing that the day is invalid | FAIL
| 5 | Delete schedule | Schedule deletion successful when the user selects a schedule and confirms the deletion | The deleted schedule is not visible in the schedule list after updated | The deleted schedule is not visible in the schedule list after updated | PASS
| 6 | Delete schedule | Schedule deletion unsuccessful when the user selects a schedule and cancels the deletion | The selected schedule is still visible in the schedule list | The selected schedule is still visible in the schedule list | PASS
US08 - I want to have terms and conditions accepted by the user before using the app - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | Figma Designs
8 | 1 | App Design Compliance | Check if the design of the app, including fonts, buttons, lists, page layouts, messages, comply with the design system elements | The app design matches the design system elements | The app design matches the design system elements | PASS
| 2 | Terms and Conditions on Register Page | On the registration page, the app's terms and conditions must be present and readable | Terms and Conditions are displayed clearly on the registration page | Terms and Conditions are displayed clearly on the registration page | PASS
| 3 | Mandatory Acceptance of Terms and Conditions | The user should not be able to complete registration without accepting the terms and conditions | Error message or indicator showing the need to accept the terms and conditions for successful registration | Error message or indicator showing the need to accept the terms and conditions for successful registration | PASS
| 4 | View Terms and Conditions | The user should be able to view the entire terms and conditions document | The entire terms and conditions document is scrollable and readable | The entire terms and conditions document is scrollable and readable | PASS
| 5 | Correct Terms and Conditions for Caregiver | The caregiver should receive the correct caregiver terms and conditions, not the patient terms and conditions | The terms and conditions provided to the caregiver match their role and not the patient's role | The terms and conditions provided to the caregiver match their role and not the patient's role | PASS
| 6 | Correct Terms and Conditions for Patient | The patient should receive the correct patient terms and conditions, not the caregiver terms and conditions | The terms and conditions provided to the patient match their role and not the caregiver's role | The terms and conditions provided to the patient match their role and not the caregiver's role | PASS
US09 - Caregiver I want to be able to sign up and login and view one or more patient(s) schedule - Siyoon
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
9 | 1 | login valid | login valid when email and password entered | login successful and go to view patients' list page | login successful and go to view patients' list page | PASS
| 2 | login invalid | login failed as email entered is invalid but password is valid | show up error message mentioning as login invalid | show up error message mentioning as login invalid | PASS
| 3 | login invalid | login failed as password entered is invalid but email is valid | show up error message mentioning as login invalid | show up error message mentioning as login invalid | PASS
| 4 | login invalid | login failed as email and passoword entered is invalid | show up error message mentioning as login invalid | show up error message mentioning as login invalid | PASS
| 5 | login invalid | login failed as user cannot be found | show up error message mentioning as user not found | show up error message mentioning as user not found | PASS
| 6 | login invalid | login failed as email entered but password not entered | show up error message mentioning as user not found | show up error message mentioning as user not found | PASS
| 7 | login invalid | login failed as password entered but email not entered | show up error message mentioning as user not found | show up error message mentioning as user not found | PASS
| 8 | view patients' list | after login, caregiver can see the list of patients who he/she manages | show up patients' list | show up patients' list | PASS
| 9 | sorrt by upcoming schedule | sort by upcoming schedule and show the list of patients in order | patients' list sorted in upcoming schedule order | patients' list sorted in upcoming schedule order | PASS
| 10 | click a patient name | click a patient name and drops options | drops options under a patient name | drops options under a patient name | PASS
| 11 | click profile option | click profile option and go to patient's profile page | go to patinet's profile page | go to patinet's profile page | PASS
| 12 | click schedule option | click schedule option and go to patient's schedule page | go to patient's schedule page | go to patient's schedule page | PASS
| 13 | click dose plan option | click dose plan option and go to patient's dose plan page | go to patient's dose plan page | go to patient's dose plan page | PASS
| 14 | click history option | click history option and go to patient's history page | go to patient's history page | go to patient's history page | PASS
| 15 | click back button in profile page | click back button and go to view patient's list page | go back to view patients' list page | no back button exists | PASS
| 16 | click back button in schedule page | click back button and go to view patient's list page | go back to view patients' list page | no back button exists | PASS
| 17 | click back button in dose plan page | click back button and go to view patient's list page | go back to view patients' list page | go back to view patients' list page | PASS
| 18 | click back button in history page | click back button and go to view patient's list page | go back to view patients' list page | no back button exists | PASS
US10 - Caregiver, I want to be able to view my patients medication history in the app - David
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
10 | 1 | CG views Patient History | App complies with the design system elements | Correct fonts are applied Correct buttons are used Correct lists are applied Correct page layout is applied Correct messages format is applied Only elements in designsystem ar eused | Correct fonts are applied Correct buttons are used Correct lists are applied Correct page layout is applied Correct messages format is applied Only elements in designsystem ar eused | FAIL | Navigation needs updating
| 2 | CG views Patient History | Caregiver can search history by date | Can search on a given date and view a patient's medication history in the app Can | View history screen for a previous date displays the scheduled dose | PASS
| 3 | CG views Patient History | App displays patient's medication history in the app | The app displays: Correct Medication name Correct Dosage amount Correct Schedule for the selected sortted by time order If the dose was taken or missed on the day. |  | PASS
| 4 | CG views Patient History | User can select a schedule to view details | The app displays: Correct Medication name Correct Dosage amount Correct Schedule for the selected sortted by time order Date and Time scheduled Date and Time taken | The app displays: Correct Medication name Correct Dosage amount Correct Schedule for the selected sortted by time order Date and Time scheduled Date and Time taken | PASS
| 5 | CG views Patient History | User trys to edit history | User unable to edit medication history | User unable to edit medication history | PASS
| 6 | CG views Patient History | User trys to delete history | User unable to deletemedication history | User unable to deletemedication history | PASS
PASS
PASS
US11 - Caregiver I want to receive notifications when the patient misses a medication dose - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
11 | 1 | App Design Compliance | Check if the design of the app, including fonts, buttons, lists, page layouts, messages, comply with the design system elements | The app design matches the design system elements | The app design matches the design system elements | PASS
| 2 | Missed Dose Notification Timing | After a dose is missed, check if a notification is sent to the caregiver after 60 minutes | Notification is sent to the caregiver 60 minutes after a dose is missed | Notification is sent to the caregiver 60 minutes after a dose is missed | PASS
| 3 | Notification Details | Check if the notification includes details about who missed the dose, when it was scheduled, and the dosage details | The notification contains all the necessary details: who missed the dose, when it was scheduled, and the dosage details | The notification contains all the necessary details: who missed the dose, when it was scheduled, and the dosage details | FAIL | Failing on what the dosage details, not present
| 4 | Online and Offline Notifications | Check if the app supports both online (app notification) and offline (text message) notifications | Caregiver receives both an online and offline notification for a missed dose | Caregiver receives both an online and offline notification for a missed dose | PASS
| 5 | Offline Notification Delivery | Check if the system sends a text message to the caregiver when the caregiver is not connected to the internet | Caregiver receives a text message about the missed dose | Caregiver receives a text message about the missed dose | PASS
US12 - As a patient, I want to be able to grant access to a caregiver - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
12 | 1 | App Design Compliance | Check if the design of the app, including fonts, buttons, lists, page layouts, messages, comply with the design system elements | The app design matches the design system elements | The app design matches the design system elements | PASS
| 2 | Grant Access to Caretaker | On the patient's settings or profile page, check if there's an option to grant access to a caretaker | Option to grant access to caretaker is visible and functional | Option to grant access to caretaker is visible and functional | PASS
| 3 | Invitation Clarity | Check the content of the invitation to ensure it includes a clear message that the patient is granting access to their health information and schedules | The invitation received by the caregiver includes a clear statement explaining that the patient is granting access to their health information and schedules | The invitation received by the caregiver includes a clear statement explaining that the patient is granting access to their health information and schedules | PASS
| 4 | Send Invitation to Caretaker | After entering the caretaker's email address or username, check if an invitation email or notification is sent to the caretaker | Caretaker receives an invitation | Caretaker receives an invitation | PASS
| 5 |  |  |  |  | PASS
| 6 | Invitations to Invalid Email | Test if system handles invalid emails when the patient tries to grant access to a caregiver | The system shows an error message stating that the email is invalid | The system shows an error message stating that the email is invalid | PASS
| 7 | Invitations to Non-registered Email | Test what happens if patient enters a non-registered email when granting access | The system shows an warning message stating that the User Account is not Found, and if the patient wants to send invitation anyway | The system shows an warning message stating that the User Account is not Found, and if the patient wants to send invitation anyway | PASS
| 8 | Revoke Access to Caretaker | Patient should be able to revoke access permissions for caretakers at any time | Caretaker loses access to the patient's schedule and relevant health information once the patient revokes access | No revoking function exists | FAIL
US13 - I want to be able to view any patient's dose list in the app - Vijay
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
13 | 1 | Dose Plan | User can select and navigate to patient dose plan from home screen. | user selcets a patient on homescreen and them clicks on dose plan from drop down menu. | Same as epected results. | PASS
| 2 | Dose Plan | Verify that the dose list is displayed in a well-organized and visually pleasing format. | The layout is properly aligned, with consistent spacing and styling of the dose list elements. Each medication details are properly segregated. | Same as epected results. | PASS
| 3 | Dose Plan | Check if medication details such as name, dosage,Interval, and route. | Medication details such as name, dosage, interval and route are clearly visible for each medication. | Same as epected results. | PASS
| 4 | Dose Plan | Ensure that the information is easily readable and distinguishable from other elements. | The information is presented in a readable format, distinguishable from other elements on the screen. | Same as epected results. | PASS
US14 - I want to be able to view any patient's profile in the app - Vijay
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
14 | 1 | Patient's Profile | Verify that the app design follows the specified design system elements, such as fonts, buttons, lists, page layouts, and messages. | Patient's profile screen follows consistent design prescribed for App. | Same as epected results. | PASS
| 2 | Patient's Profile | Verify that the profile displayed corresponds to the selected patient. | user selcets a patient on homescreen and them clicks on dose plan from drop down menu. | Same as epected results. | PASS
| 3 | Patient's Profile | Check that the patient's profile information (Patient name, contact number, email address, D.O.B, Assinged GP, NHI) is accurate and matches the expected details. | All pateint deatails are correct. | Same as epected results. | PASS
| 4 | Patient's Profile | Attempt to edit any field in the patient's profile. | Fields are not editable, no edit button is displayed on screen. | Same as epected results. | PASS
| 5 | Patient's Profile | Attempt to delete the patient's profile. | No delete button is displayed, User not able to delete patient's profile | Same as epected results. | PASS
VK
VK
BT
BT
BT
BT
SJ
DH
VK

## S1 Test Cycle 2
SPRINT 1 TEST CASES
US06 - I want to make the designs more consistent accross all screens - Vijay
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
6 | 1 | App Design - Color consistency. | Verify that the color palette used is consistent across screens. | The color palette used across all screens is consistent, with primary, secondary, and accent colors applied uniformly. | Same as expected Results | Pass
| 2 | App Design - Color consistency. | Check for any color variations or deviations that might impact design consistency | There are no color variations or deviations that impact design consistency. | Same as expected Results | Pass
| 3 | App Design - Typography consistency. | Check for any variations in headings, body text, and other typographic elements. | Font styles (typeface, size, weight) are consistent throughout the application. Headings, body text, and other typographic elements adhere to the defined style guide | Same as expected Results | Pass
| 4 | App Design - Typography consistency. | Ensure that typography follows the defined style guide and enhances readability. | Adhere to the defined style guide, enhancing readability and maintaining consistency. | Same as expected Results | Pass
| 5 | App Design - Alignment spacing consistency | Verify that alignment (horizontal and vertical) is consistent across screens. | UI elements on each screen exhibit consistent alignment, both horizontally and vertically | Same as expected Results | Pass
| 6 | App Design - Alignment spacing consistency | Check if spacing between elements (margins, padding) is consistent and visually balanced. | Spacing between elements (margins, padding) is visually balanced and consistently applied. The layout adheres to grids and guidelines defined in the design system. | Same as expected Results | Pass
| 7 | App Design -iconography consistency | Review the use of icons on different screens. | The same set of icons is consistently used across different screens of the application. | Same as expected Results | Pass
| 8 | App Design -iconography consistency | Verify that the same set of icons is consistently used throughout the application. | The same set of icons is consistently used across different screens of the application. | Same as expected Results | Pass
| 9 | App Design -iconography consistency | Check for any variations in icon styles, sizes, or shapes. |  | Same as expected Results | Pass
| 10 |  |  | Icon styles, sizes, and shapes remain consistent | Same as expected Results | Pass
| 11 | App Design -iconography consistency | Ensure that icons are aligned with the overall visual language and design principles. | Aligning with the overall visual language and design principles. | Same as expected Results | Pass
[5 empty] | Same as expected Results | Pass
| 12 | App Design - button and form element consistency | Check if form elements (input fields, buttons) have a consistent appearance. | Form elements, including input fields, checkboxes, and buttons, maintain a consistent appearance. | Same as expected Results | Pass
| 13 | App Design - button and form element consistency | Verify that button styles (size, shape, color) are consistent across screens. | Button styles (size, shape, color) are consistent across screens, providing a cohesive look and feel. | Same as expected Results | Pass
| 14 | App Design - button and form element consistency | Navigate to screens that contain buttons and form elements. | Interactions such as focus behave consistently for buttons and form elements. | Same as expected Results | Pass
| 15 | App Design - Error and feedback messages consistency: | Verify that error messages and feedback notifications are consistent. | Error messages and feedback notifications maintain consistency in terms of color, typography, and placement. | Same as expected Results | Pass
| 16 | App Design - Error and feedback messages consistency: | Check for any variations in color, typography, or placement of error messages. | consistency in terms of color, typography, and placement. | Same as expected Results | Pass
| 17 | App Design - Error and feedback messages consistency: | Ensure that error messages provide clear and actionable information. | Provides clear and actionable information consistently across screens, ensuring a seamless user experience. | Same as expected Results | Pass
| 18 | App Design - validate navigation consistency. | Navigate through different screens using the application's navigation. | There are no variations in navigation styles, placement, or interaction patterns. | Same as expected Results | Pass
| 19 | App Design - validate navigation consistency. | Verify that the navigation elements are consistent. | The navigation elements are consistent across screens. | Same as expected Results | Pass
| 20 | App Design - validate navigation consistency. | Check for any variations in navigation styles, placement, | There are no variations in navigation styles, placement, or interaction patterns. | Same as expected Results | Pass
| 21 | App Design - validate navigation consistency. | Ensure that users can easily navigate between screens without confusion. | Users can easily navigate between screens without confusion. | Same as expected Results | Pass
US07 - As a Patient, I want to be able to edit or delete my schedule - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
7 | 1 | Edit Schedule | Patient tap on a schedule in schedule list to edit or delete | The edit schedule page displayed with all information about the chosen schedule | The edit schedule page displayed with all information about the chosen schedule | PASS
| 2 | Edit Schedule | Patient selects and edit medication name, dosage, time,... then saves | User sees updated medication name, time, day, frequency in the schedule list | User sees updated medication name, time, day, frequency in the schedule list | PASS
| 3 | Edit schedule | Schedule edit fails when the user tries to save without providing the medication name | Show an error message stating that the medication name is required | No error message showing that the medication name is required | PASS
| 4 | Edit schedule | Schedule edit fails when user tries to save with invalid day (day in the past) | Show an error message stating that the day is invalid | No error message showing that the day is invalid | PASS
| 5 | Delete schedule | Schedule deletion successful when the user selects a schedule and confirms the deletion | The deleted schedule is not visible in the schedule list after updated | The deleted schedule is not visible in the schedule list after updated | PASS
| 6 | Delete schedule | Schedule deletion unsuccessful when the user selects a schedule and cancels the deletion | The selected schedule is still visible in the schedule list | The selected schedule is still visible in the schedule list | PASS
US08 - I want to have terms and conditions accepted by the user before using the app - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | Figma Designs
8 | 1 | App Design Compliance | Check if the design of the app, including fonts, buttons, lists, page layouts, messages, comply with the design system elements | The app design matches the design system elements | The app design matches the design system elements | PASS
| 2 | Terms and Conditions on Register Page | On the registration page, the app's terms and conditions must be present and readable | Terms and Conditions are displayed clearly on the registration page | Terms and Conditions are displayed clearly on the registration page | PASS
| 3 | Mandatory Acceptance of Terms and Conditions | The user should not be able to complete registration without accepting the terms and conditions | Error message or indicator showing the need to accept the terms and conditions for successful registration | Error message or indicator showing the need to accept the terms and conditions for successful registration | PASS
| 4 | View Terms and Conditions | The user should be able to view the entire terms and conditions document | The entire terms and conditions document is scrollable and readable | The entire terms and conditions document is scrollable and readable | PASS
| 5 | Correct Terms and Conditions for Caregiver | The caregiver should receive the correct caregiver terms and conditions, not the patient terms and conditions | The terms and conditions provided to the caregiver match their role and not the patient's role | The terms and conditions provided to the caregiver match their role and not the patient's role | PASS
| 6 | Correct Terms and Conditions for Patient | The patient should receive the correct patient terms and conditions, not the caregiver terms and conditions | The terms and conditions provided to the patient match their role and not the caregiver's role | The terms and conditions provided to the patient match their role and not the caregiver's role | PASS
US09 - Caregiver I want to be able to sign up and login and view one or more patient(s) schedule - Siyoon
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
9 | 1 | login valid | login valid when email and password entered | login successful and go to view patients' list page | login successful and go to view patients' list page | PASS
| 2 | login invalid | login failed as email entered is invalid but password is valid | show up error message mentioning as login invalid | show up error message mentioning as login invalid | PASS
| 3 | login invalid | login failed as password entered is invalid but email is valid | show up error message mentioning as login invalid | show up error message mentioning as login invalid | PASS
| 4 | login invalid | login failed as email and passoword entered is invalid | show up error message mentioning as login invalid | show up error message mentioning as login invalid | PASS
| 5 | login invalid | login failed as user cannot be found | show up error message mentioning as user not found | show up error message mentioning as user not found | PASS
| 6 | login invalid | login failed as email entered but password not entered | show up error message mentioning as user not found | show up error message mentioning as user not found | PASS
| 7 | login invalid | login failed as password entered but email not entered | show up error message mentioning as user not found | show up error message mentioning as user not found | PASS
| 8 | view patients' list | after login, caregiver can see the list of patients who he/she manages | show up patients' list | show up patients' list | PASS
| 9 | sorrt by upcoming schedule | sort by upcoming schedule and show the list of patients in order | patients' list sorted in upcoming schedule order | patients' list sorted in upcoming schedule order | PASS
| 10 | click a patient name | click a patient name and drops options | drops options under a patient name | drops options under a patient name | PASS
| 11 | click profile option | click profile option and go to patient's profile page | go to patinet's profile page | go to patinet's profile page | PASS
| 12 | click schedule option | click schedule option and go to patient's schedule page | go to patient's schedule page | go to patient's schedule page | PASS
| 13 | click dose plan option | click dose plan option and go to patient's dose plan page | go to patient's dose plan page | go to patient's dose plan page | PASS
| 14 | click history option | click history option and go to patient's history page | go to patient's history page | go to patient's history page | PASS
| 15 | click back button in profile page | click back button and go to view patient's list page | go back to view patients' list page | no back button exists | PASS
| 16 | click back button in schedule page | click back button and go to view patient's list page | go back to view patients' list page | no back button exists | PASS
| 17 | click back button in dose plan page | click back button and go to view patient's list page | go back to view patients' list page | go back to view patients' list page | PASS
| 18 | click back button in history page | click back button and go to view patient's list page | go back to view patients' list page | no back button exists | PASS
US10 - Caregiver, I want to be able to view my patients medication history in the app - David
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
10 | 1 | CG views Patient History | App complies with the design system elements | Correct fonts are applied Correct buttons are used Correct lists are applied Correct page layout is applied Correct messages format is applied Only elements in designsystem ar eused | Correct fonts are applied Correct buttons are used Correct lists are applied Correct page layout is applied Correct messages format is applied Only elements in design system are used | PASS
| 2 | CG views Patient History | Caregiver can search history by date | Can search on a given date and view a patient's medication history in the app Can | View history screen for a previous date displays the scheduled dose | PASS
| 3 | CG views Patient History | App displays patient's medication history in the app | The app displays: Correct Medication name Correct Dosage amount Correct Schedule for the selected sortted by time order If the dose was taken or missed on the day. |  | PASS
| 4 | CG views Patient History | User can select a schedule to view details | The app displays: Correct Medication name Correct Dosage amount Correct Schedule for the selected sortted by time order Date and Time scheduled Date and Time taken | The app displays: Correct Medication name Correct Dosage amount Correct Schedule for the selected sortted by time order Date and Time scheduled Date and Time taken | PASS
| 5 | CG views Patient History | User trys to edit history | User unable to edit medication history | User unable to edit medication history | PASS
| 6 | CG views Patient History | User trys to delete history | User unable to deletemedication history | User unable to deletemedication history | PASS
PASS
PASS
US11 - Caregiver I want to receive notifications when the patient misses a medication dose - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
11 | 1 | App Design Compliance | Check if the design of the app, including fonts, buttons, lists, page layouts, messages, comply with the design system elements | The app design matches the design system elements | The app design matches the design system elements | PASS
| 2 | Missed Dose Notification Timing | After a dose is missed, check if a notification is sent to the caregiver after 60 minutes | Notification is sent to the caregiver 60 minutes after a dose is missed | Notification is sent to the caregiver 60 minutes after a dose is missed | PASS
| 3 | Notification Details | Check if the notification includes details about who missed the dose, when it was scheduled, and the dosage details | The notification contains all the necessary details: who missed the dose, when it was scheduled, and the dosage details | The notification contains all the necessary details: who missed the dose, when it was scheduled, and the dosage details | PASS
| 4 | Online and Offline Notifications | Check if the app supports both online (app notification) and offline (text message) notifications | Caregiver receives both an online and offline notification for a missed dose | Caregiver receives both an online and offline notification for a missed dose | PASS
| 5 | Offline Notification Delivery | Check if the system sends a text message to the caregiver when the caregiver is not connected to the internet | Caregiver receives a text message about the missed dose | Caregiver receives a text message about the missed dose | PASS
US12 - As a patient, I want to be able to grant access to a caregiver - Benny
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
12 | 1 | App Design Compliance | Check if the design of the app, including fonts, buttons, lists, page layouts, messages, comply with the design system elements | The app design matches the design system elements | The app design matches the design system elements | PASS
| 2 | Grant Access to Caretaker | On the patient's settings or profile page, check if there's an option to grant access to a caretaker | Option to grant access to caretaker is visible and functional | Option to grant access to caretaker is visible and functional | PASS
| 3 | Invitation Clarity | Check the content of the invitation to ensure it includes a clear message that the patient is granting access to their health information and schedules | The invitation received by the caregiver includes a clear statement explaining that the patient is granting access to their health information and schedules | The invitation received by the caregiver includes a clear statement explaining that the patient is granting access to their health information and schedules | PASS
| 4 | Send Invitation to Caretaker | After entering the caretaker's email address or username, check if an invitation email or notification is sent to the caretaker | Caretaker receives an invitation | Caretaker receives an invitation | PASS
| 5 |  |  |  |  | PASS
| 6 | Invitations to Invalid Email | Test if system handles invalid emails when the patient tries to grant access to a caregiver | The system shows an error message stating that the email is invalid | The system shows an error message stating that the email is invalid | PASS
| 7 | Invitations to Non-registered Email | Test what happens if patient enters a non-registered email when granting access | The system shows an warning message stating that the User Account is not Found, and if the patient wants to send invitation anyway | The system shows an warning message stating that the User Account is not Found, and if the patient wants to send invitation anyway | PASS
| 8 | Revoke Access to Caretaker | Patient should be able to revoke access permissions for caretakers at any time | Caretaker loses access to the patient's schedule and relevant health information once the patient revokes access | No revoking function exists | PASS
US13 - I want to be able to view any patient's dose list in the app - Vijay
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
13 | 1 | Dose Plan | User can select and navigate to patient dose plan from home screen. | user selcets a patient on homescreen and them clicks on dose plan from drop down menu. | Same as epected results. | PASS
| 2 | Dose Plan | Verify that the dose list is displayed in a well-organized and visually pleasing format. | The layout is properly aligned, with consistent spacing and styling of the dose list elements. Each medication details are properly segregated. | Same as epected results. | PASS
| 3 | Dose Plan | Check if medication details such as name, dosage,Interval, and route. | Medication details such as name, dosage, interval and route are clearly visible for each medication. | Same as epected results. | PASS
| 4 | Dose Plan | Ensure that the information is easily readable and distinguishable from other elements. | The information is presented in a readable format, distinguishable from other elements on the screen. | Same as epected results. | PASS
US14 - I want to be able to view any patient's profile in the app - Vijay
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
14 | 1 | Patient's Profile | Verify that the app design follows the specified design system elements, such as fonts, buttons, lists, page layouts, and messages. | Patient's profile screen follows consistent design prescribed for App. | Same as epected results. | PASS
| 2 | Patient's Profile | Verify that the profile displayed corresponds to the selected patient. | user selcets a patient on homescreen and them clicks on dose plan from drop down menu. | Same as epected results. | PASS
| 3 | Patient's Profile | Check that the patient's profile information (Patient name, contact number, email address, D.O.B, Assinged GP, NHI) is accurate and matches the expected details. | All pateint deatails are correct. | Same as epected results. | PASS
| 4 | Patient's Profile | Attempt to edit any field in the patient's profile. | Fields are not editable, no edit button is displayed on screen. | Same as epected results. | PASS
| 5 | Patient's Profile | Attempt to delete the patient's profile. | No delete button is displayed, User not able to delete patient's profile | Same as epected results. | PASS
VK
VK
BT
BT
BT
BT
SJ
DH
VK

## S1 Burndown
BURNDOWN CHART
DAY / SPRINT / ITERATION | FEATURES / STORY POINTS GOAL | COMPLETE | GOAL VELOCITY | REMAINING
0 | 0 | 0
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 3 | 0 | -3 | 0
4 | 3 | 0 | -6 | 0
5 | 3 | 2 | -9 | -2
6 | 3 | 3 | -12 | -5
7 | 3 | 6 | -15 | -11
8 | 3 | 8 | -18 | -19
9 | 3 | 0 | -21 | -19
10 | 4 | 3 | -25 | -22
Total | 25 | 19

## S1 Retro
SPRINT 1 RETROSPECTIVE
Sprint Goal: Create wireframes and test customer journeys and designs, write and execute test cases for top 5 priority user stories.
WHAT WENT WELL | WHAT DIDN’T GO WELL | WHAT COULD BE IMPROVED
Daily Scrum in Whats App
Whats App group chat
More attention to design required, prototype had issues, rework
User story is complex
Agreeing on design for grant access
Reduce rework
Work estimation was accurate
Achieving deadline
Design system
Communication in ceremonies and whats app
More amount of work has been done
More consistent designs overall
Wireframe takes long to complete and adjust
Precise test cases, failed test cases and 2 test cycles
Complexity of user grant access stories
Need more standards to follow
Rework required for complex stories
Breakdown complex user story in detail
Team were familiar with process
Implemented regular Daily Scrum
Achieved more user stories than Sprint 0 - increased velocity 166%
Improved quality of designs and prototype
Dependencies between user story designs blocked other stories
Competing priorites with written test and other assignments
Timekeeping on Daily Scrum was a bit loose
More meetings in person
More story refinement incl low fidelity wires before design starts
Well organised Sprint Plan

## Sprint Plan
SPRINT DATES
SPRINT | SPRINT START |  |  | FINISH | SPRINT DAYS | POINTS PLANNED | POINTS ACHIEVED | VELOCITY | NOTES AND COMMENTS
Sprint 0 | 2023-05-01 |  |  | 2023-05-10 | 9 | 15 | 15 | 15 | Sprint 0
Sprint 1 | 2023-05-29 |  |  | 2023-06-09 | 10 | 25 | 25 | 25 | Sprint 1
Total |  |  |  |  | 19 | 40 | 40 | 40
Average | [7 empty] | 20
Class | Week |  |  | Week | Milestone |  |  |  | Comments
2023-03-02 |  |  |  | Wk1 | DONE
2023-03-09 |  |  |  | Wk2 | DONE
2023-03-16 |  |  |  | Wk3 | DONE
2023-03-23 |  |  |  | Wk4 | DONE
2023-03-30 |  |  |  | Wk5 | DONE
2023-04-06 |  |  |  | Wk6 | DONE
2023-04-27 |  |  |  | Wk7 | DONE
2023-05-04 | Sprint 0 |  |  | Wk8 | DONE |  |  |  | Sprint 0
2023-05-11 | Sprint 0 |  |  | Wk9 | DONE |  |  |  | Sprint 0
2023-05-18 |  | Planning | Planning | Wk10 | DONE |  |  |  | No Class
2023-05-25 | Planning | Sprint 1 | Sprint 1 | Wk11 | DONE |  |  |  | No Class
2023-06-01 | Sprint 1 | Sprint 1 | Sprint 1 | Wk12 | DONE |  |  |  | No Class
2023-06-08 | Sprint 1 | Sprint 1 |  | Wk13 | DONE |  |  |  | TIn Class - Written Test
2023-06-15 | Present | Present | Present | Wk14 | Milestone 5 – Sprint Review and Retrospective presentation (due Week 14) Milestone 6 –Peer evaluation form (due Week 14) |  |  |  | Assignment Presentation
2023-06-22 |  |  |  | Wk15
Formulas:
SPRINT = [SPRINT, row below]-7
SPRINT = [SPRINT, row above]+7

## S0 Retro
SPRINT 0 RETROSPECTIVE
Sprint Goal: Create wireframes and test customer journeys and designs, write and execute test cases for top 5 priority user stories.
WHAT WENT WELL | WHAT DIDN’T GO WELL | WHAT COULD BE IMPROVED
Cross-functional team able to perform multiple roles
Sprint planning meeting was collaborative
Less tickets moved to DONE in Wk1
Shortened Sprint to 9 days
Target designs done at end of week 1
Design system developed up front to get consistency
Quality end result designs
Designs user tested by person in industry
Daily comms in WhatsApp
Bi-weekly standups
Meet in person on Thursdays
Testing improved designs
Misalignment on designs layout caused some rework
Completed all committed user stories
More specific acceptance criteria
Prioritisation of user stories changed alot pre sprint
Avoid duplication and overlaps of user stories in backlog
Design didnt cover all possible scenerios
Hard to guage status of tasks on board (not all of Team moving storied )
Good time management
Well organised Sprint Plan
Team respected others ideas, listened first and discuss later
Allocating points to user story
All requirements submitted on time

## S0 Backlog
Sprint Backlog
Sprint Goal: Create wireframes and test customer journeys and designs, write and execute test cases for top 5 priority user stories.
ASSIGNED TO | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
DH
SJ
BT
User Story 1 - Create Wireframes
STATUS: Not Started
User Story 1 - execute test case
STATUS: Not Started
User Story 2 - Create Wireframes/ UI Design
STATUS: Not Started
User Story 3 - Create Wireframes/ UI Design
STATUS: Not Started
User Story 5 - Create Wireframes/ UI Design
STATUS: Not Started
User Story 1 - Write test cases
STATUS: Not Started
User Story 2 - Write test cases
STATUS: Not Started
User Story 4 - Write test cases
STATUS: Not Started
User Story 5 - Write test cases
STATUS: Not Started
User Story 2 - execute test case
STATUS: Not Started
User Story 3 - execute test case
STATUS: Not Started
User Story 4 - execute test case
STATUS: Not Started
User Story 5 - execute test case
STATUS: Not Started
VK
DH
SJ
BT
VK
DH
BT
DH
SJ
VK
DH
SJ
VK
DH
SJ
VK
User Story 3 - Write test cases
STATUS: Not Started
User Story 4 - Create Wireframes/ UI Design
STATUS: Not Started
Customer testing of wireframes and customer journey
STATUS: Not Started
Create Everdose Logo and splash people
STATUS: Not Started
Create Sprint 0 Presentation
STATUS: Not Started
Create Homepage Screen
STATUS: Not Started
SJ

## S0 Planning
SPRINT 0 TASK BOARD
Sprint Goal: Create wireframes and test customer journeys and designs, write and execute test cases for top 5 priority user stories.
ASSIGNED TO | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
DH
SJ
BT
User Story 1 - Create Wireframes
STATUS: Not Started
User Story 1 - execute test case
STATUS: Not Started
User Story 2 - Create Wireframes/ UI Design
STATUS: Not Started
User Story 3 - Create Wireframes/ UI Design
STATUS: Not Started
User Story 5 - Create Wireframes/ UI Design
STATUS: Not Started
User Story 1 - Write test cases
STATUS: Not Started
User Story 2 - Write test cases
STATUS: Not Started
User Story 4 - Write test cases
STATUS: Not Started
User Story 5 - Write test cases
STATUS: Not Started
User Story 2 - execute test case
STATUS: Not Started
User Story 3 - execute test case
STATUS: Not Started
User Story 4 - execute test case
STATUS: Not Started
User Story 5 - execute test case
STATUS: Not Started
VK
DH
SJ
BT
VK
DH
BT
DH
SJ
VK
DH
SJ
BT
VK
DH
SJ
BT
VK
BT
VK
User Story 3 - Write test cases
STATUS: Not Started
VK
User Story 4 - Create Wireframes/ UI Design
STATUS: Not Started
Customer testing of wireframes and customer journey
STATUS: Not Started
VK
Create Everdose Logo and splash people
STATUS: Not Started
VK
VK
Create Sprint 0 Presentation
STATUS: Not Started
DH
SJ
BT
Create Homepage Screen
STATUS: Not Started
SJ
SJ

## S0 Wk1
SPRINT 0 TASK BOARD
Sprint Goal: Create wireframes and test customer journeys and designs, write and execute test cases for top 5 priority user stories.
ASSIGNED TO | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
DH
SJ
BT
User Story 1 - Create Wireframes
STATUS: DONE
User Story 1 - execute test case
STATUS: Not Started
User Story 2 - Create Wireframes/ UI Design
STATUS: DONE
User Story 3 - Create Wireframes/ UI Design
STATUS: DONE
User Story 5 - Create Wireframes/ UI Design
STATUS: DONE
User Story 1 - Write test cases
STATUS: Not Started
User Story 2 - Write test cases
STATUS: DONE
User Story 4 - Write test cases
STATUS: In Progress
User Story 5 - Write test cases
STATUS: In Progress
User Story 2 - execute test case
STATUS: Not Started
User Story 3 - execute test case
STATUS: Not Started
User Story 4 - execute test case
STATUS: Not Started
User Story 5 - execute test case
STATUS: Not Started
VK
DH
SJ
BT
VK
BT
DH
SJ
VK
DH
SJ
BT
VK
DH
SJ
BT
VK
BT
VK
User Story 3 - Write test cases
STATUS: DONE
VK
User Story 4 - Create Wireframes/ UI Design
STATUS: In Progress
Customer testing of wireframes and customer journey
STATUS: Not Started
VK
Create Everdose Logo and splash people
STATUS: In Progress
VK
VK
Create Sprint 0 Presentation
STATUS: Not Started
DH
Create Homepage Screen
STATUS: In Progress
SJ
SJ
SJ
BT
SJ

## S0 Wk2
SPRINT 0 TASK BOARD
Sprint Goal: Create wireframes and test customer journeys and designs, write and execute test cases for top 5 priority user stories.
ASSIGNED TO | BACKLOG TASKS | TO DO | IN PROGRESS | DONE
DH
SJ
BT
User Story 1 - Create Wireframes
STATUS: DONE
User Story 1 - execute test case
STATUS: DONE
User Story 2 - Create Wireframes/ UI Design
STATUS: DONE
User Story 3 - Create Wireframes/ UI Design
STATUS: DONE
User Story 1 - Write test cases
STATUS: DONE
User Story 2 - Write test cases
STATUS: DONE
User Story 4 - Write test cases
STATUS: DONE
User Story 5 - Write test cases
STATUS: DONE
User Story 2 - execute test case
STATUS: DONE
User Story 5 - execute test case
STATUS: DONE
VK
DH
BT
VK
BT
DH
SJ
VK
DH
SJ
BT
VK
DH
SJ
BT
VK
BT
VK
User Story 3 - Write test cases
STATUS: DONE
VK
Customer testing of wireframes and customer journey
STATUS: DONE
VK
Create Everdose Logo and splash people
STATUS: DONE
VK
VK
Create Sprint 0 Presentation
STATUS: DONE
DH
BT
User Story 5 - Create Wireframes/ UI Design
STATUS: DONE
SJ
Create Homepage Screen
STATUS: DONE
SJ
User Story 4 - Create Wireframes/ UI Design
STATUS: DONE
SJ
User Story 3 - execute test case
STATUS: DONE
SJ
User Story 4 - execute test case
STATUS: DONE
SJ

## S0 Test Cases
TEST CASES
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | 1 | Login - valid | Correct Email and Password entered on the log in screen | The app opens Home Page | The app opens Home Page | PASS
| 2 | Login - invalid | Incorrect Password entered on the log in screen | "Incorrect Password" message returned when click on Log in button | "Incorrect Email or Password" message returned when click on Log in button | PASS
| 3 | Login - unregistered | unregistered Email or Password entered on the log in screen | "User not found" message return when click on Log in button | "User not found" message return when click on Log in button | PASS
| 4 | Login - Signup button | User clicks on the Signup link on Login page | The app opens Signup page | The app opens Signup page | PASS
| 5 | Login - Forgot Password button | User Clicks on the Forgot Password link on Login Page | The app open Forgot Password Page | The app open Forgot Password Page | PASS
| 6 | Signup - valid | Register with valid information (formatted email, valid phone number, valid password length) | "Signup successfully" message returned when click on sign-up button | "Signup successfully" message returned when click on signup button | PASS
| 7 | Signup - invalid | Register with invalid information (email, phone number, password) | Registration failed, "Invalid email address, phone number or password length" message returned when click on signup button | Registration failed, "Invalid email address, phone number or password length" message returned when click on signup button | PASS
| 8 | Signup - Login button | User clicks on the Login link on Signup page | The app opens Login page | The app opens Login page | PASS
| 9 | Forgot password - valid | Enter correct email and last used password | "Recovery Link sent successfully, please check your mail" message returned when click on Send button | "Recovery Link sent successfully, please check your mail" message returned when click on Send button | PASS
| 10 | Forgot password - invalid | Enter incorrect email | "User not found, failed to reset password" message return when click on send button | "User not found, failed to reset password" message return when click on send button | PASS
| 11 | Forgot password - Signup button | User clicks on the Signup link on Forgot Password page | The app opens Signup page | The app opens Signup page | PASS
| 12 | Forgot password - Login button | User clicks on the Login link on Forgot Password page | The app opens Login page | The app opens Login page | PASS
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
2 | 1 | Add Schedule | Title field - User clicks on “Title” field. | User can edit title field; phone keyboard is displayed. | Same as the expected result. | PASS
| 2 | Add Schedule | Date field - User clicks on “Date” field. | Date picker is displayed. | Same as the expected result. | PASS
| 3 | Add Schedule | Time field - User clicks on “Time” field. | Time picker is displayed. | Same as the expected result. | PASS
| 4 | Add Schedule | Occurrence field - User clicks on “reminder notification” field. | Dropdown list is displayed with list of options (Daily, weekdays, every day, fortnightly and monthly). | Same as the expected result. | PASS
| 5 | Add Schedule | Reminder notification - User clicks on “reminder notification” field. | Drop down list is displayed with list options (5,10,15,20,30,45 minutes) | Same as the expected result. | PASS
| 6 | Add Schedule | Medication List field - User clicks on “Add from list” field. | Drop down list of saved medication is displayed. | Same as the expected result. | PASS
| 7 | Add Schedule | Dose field - User clicks on “Dose” field. | Drop down list is displayed with list option of numbering ranging from 5 to 1000. | Same as the expected result. | PASS
| 8 | Add Schedule | Notes field - User clicks on “Notes” field and enters. | User can edit note field, phone keyboard is displayed. | Same as the expected result. | PASS
| 9 | Add Schedule | Discard button - User clicks on “Discard” button. | App don’t save any information entered by the user and returns to home page. | Same as the expected result. | PASS
| 10 | Add Schedule | Save Button - User clicks on “Save” button. | App saves the schedule and displays message “Your Schedule is added successfully!”. Add another schedule button is displayed. | Same as the expected result. | PASS
| 11 | Add Schedule | Add Another Schedule button - User clicks on “Add another Schedule” button. | App displays the “Add Schedule” page. | Same as the expected result. | PASS
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | Figma Designs
3 | 1 | View History | User selects "History" in bottom nav bar. | App displays "view history page". App displays past schedules in ascending order. | Same as the expected result. | PASS
| 2 | View History | Date picker displayed at the top. | User selects desired date from date picker, app displays history starting from that date. | Same as the expected result. | PASS
| 3 | View History | Past schedule information displayed. | Contains time, medication time taken and dose information is displayed correctly for each past schedule. | Same as the expected result. | PASS
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
4 | 1 | Submit intake | User selects intake in bottom nav bar | App displays the Submit Intake screen defaulted to todays date. App diaplys the screen as per the Figmas designs. | App displays the Submit Intake screen defaulted to today's date. App displays the screen as per the Figmas designs. | PASS
| 2 | Submit intake | User selects to submit a dose. | App displays the second Submit Intake screen displaying the right medication, right time and right dose as the user selection. App displays the screen as per the Figmas designs. | App displays the second Submit Intake screen displaying the right medication, right time and right dose as the user selection. App displays the screen as per the Figmas designs. | PASS
| 3 | Submit intake | User selects to Submit Intake button | App displays the third Submit Intake screen displaying the message 'Your intake is submitted successfully'. App displays the screen as per the Figmas designs. | App displays the third Submit Intake screen displaying the message 'Your intake is submitted successfully'. App displays the screen as per the Figmas designs. | PASS
| 4 | Submit intake | User selects to Sumit another dose button | Apps displays the first Submit Intake screen and status has been updated to show the dose has been taken. App displays the screen as per the Figmas designs. | Apps displays the first Submit Intake screen and status has been updated to show the dose has been taken. App displays the screen as per the Figmas designs. | PASS
| 5 | Submit intake | User repeats steps 1 to 4 above and then presses the Complete Intake button | User is returned to the home screen and the correct status is shown for the submitted intake | User is returned to the home screen and the correct status is shown for the submitted intake | PASS
| 6 | Submit intake | User selects to submit intake for a future date/ time greater than 30 minutes | App returns error message 'date and time is in the future' Sumit intake is not recorded | App returns error message 'date and time is in the future' Sumit intake is not recorded | PASS
| 7 | Submit intake | User selects to submit intake for a past date/ time | App accepts the submission | App accepts the submission | PASS
| 8 | Submit intake | User selects to Complete Intake button on screen 3 | User is returned to the home screen and the correct status is shown for the submitted intake | User is returned to the home screen and the correct status is shown for the submitted intake | PASS
| 9 | Submit intake | User does not press Submit Intake button on screen 2 and navigate to the home page | Submit intake is not updated. User is returned to the home screen and the correct status is shown for the selected dates/ time | Submit intake is not updated. User is returned to the home screen and the correct status is shown for the selected dates/ time | PASS
USER STORY # | TEST CASE # | FUNCTIONALITY | TEST DESCRIPTION | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | FIGMA DESIGNS
5 | 1 | Receive reminders | User adds schedule with a 5 min reminder for a future date/ time intake | App displays a reminder on patient's phone as per the Figma designs 5 minutes prior to the medication is due. The reminder display time medication is due. | App displays a reminder on patient's phone as per the Figma designs 5 minutes prior to the medication is due. The reminder display time medication is due. | PASS
| 2 | Receive reminders | User adds schedule with a 10 min reminder for a future date/ time intake | App displays a reminder on patient's phone as per the Figma designs 10 minutes prior to the medication is due. The reminder display time medication is due. | App displays a reminder on patient's phone as per the Figma designs 10 minutes prior to the medication is due. The reminder display time medication is due. | PASS
| 3 | Receive reminders | User adds schedule with a 15 min reminder for a future date/ time intake | App displays a reminder on patient's phone as per the Figma designs 5 minutes prior to the medication is due. The reminder display time medication is due. | App displays a reminder on patient's phone as per the Figma designs 5 minutes prior to the medication is due. The reminder display time medication is due. | PASS
| 4 | Receive reminders | User adds schedule with a 20 min reminder for a future date/ time intake | App displays a reminder on patient's phone as per the Figma designs 20 minutes prior to the medication is due. The reminder display time medication is due. | App displays a reminder on patient's phone as per the Figma designs 20 minutes prior to the medication is due. The reminder display time medication is due. | PASS
| 5 | Receive reminders | User adds schedule with a 30 min reminder for a future date/ time intake | App displays a reminder on patient's phone as per the Figma designs 30 minutes prior to the medication is due. The reminder display time medication is due. | App displays a reminder on patient's phone as per the Figma designs 30 minutes prior to the medication is due. The reminder display time medication is due. | PASS
| 6 | Receive reminders | User adds schedule with a 60 min reminder for a future date/ time intake | App displays a reminder on patient's phone as per the Figma designs 60 minutes prior to the medication is due. The reminder display time medication is due. | App displays a reminder on patient's phone as per the Figma designs 60 minutes prior to the medication is due. The reminder display time medication is due. | PASS
| 7 | Receive reminders | User adds schedule with no reminder | App accepts no reminders as a valid selection No reminders are returned prior to the intake due time/ date | App accepts no reminders as a valid selection No reminders are returned prior to the intake due time/ date | PASS
| 8 | Receive reminders | User adds schedule with a 5 min reminder for 3 medications all at the same future date/ time intake | The reminder lists all the medication due for that specific time. | The reminder lists all the medication due for that specific time. | PASS

## S0 Burndown
BURNDOWN CHART
DAY / SPRINT / ITERATION | FEATURES / STORY POINTS GOAL | COMPLETE | GOAL VELOCITY | REMAINING
0 | 0 | 0
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 3 | 0 | -3 | 0
4 | 0 | 0 | -3 | 0
5 | 3 | 0 | -6 | 0
6 | 0 | 6 | -6 | -6
7 | 3 | 6 | -9 | -12
8 | 3 | 3 | -12 | -15
9 | 3 | 0 | -15 | -15
Total | 15 | 15

## Milestones (hidden)
Miletone 3
Sprint planning, and backlog grooming (due on week 7 and week 11)
Milestone 3 - Sprint planning, and backlog grooming (due on week 7 and week 11) a) Before the class, pick top 5 priority user stories and write acceptance criteria, break into tasks, enter these into YouTrack. b) During the class, your team will be given time to read out some of your acceptance criteria and tasks and receive feedback. c) During the class, your team will be given time to perform planning poker to add estimates (story points) to the backlog. d) During the class, your team will select several user stories to commit to the Sprint. e) During the class, your team will define the goals for the Sprint and enter into an Agile boardGitlab Wiki.
Miletone 4
Develop the software, and apply Agile and Lean practices
In each Sprint, deliver the user stories that you committed to the sprint backlog – including writing tests, writing code, running tests, and deploying your code. b) In real-life projects, Standup meetings should be run daily. For the purpose of the group assignment, you should run at least 2 stand up meetings each week to track progress. These meetings can be completed in person, or over the phone/instant messaging for teams that cannot meet physically. ScrumMaster should note down impediments at each Standup Meeting and tick off when completed. c) Incorporate some Agile and Lean practices of your choice, such as pair programming, TDD, architectural spikes, refactoring, test automation, limiting work-in-progress.

## Agile Sprint TASKS with Kanban (hidden)
AGILE SPRINT WITH KANBAN BOARD TEMPLATE
SPRINT START DATE |  |  | DAYS | PROGRESS | THIS SPRINT
MM/DD/YY |  |  | 63 | 52% | 25
TASKS | Fill in the spreadsheet below. Then, use the tools on the Kanban Template Tab of this document to copy and paste Kanban cards and personnel icons to the Tasks Kanban board below this table.
CATEGORY | ROLE | ASSIGNED TO | ACTION | RATIONALE | STATUS | PRIORITY | POINTS | HOURS | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Feature | Team | Leon W | Project Charter | Reason 1 | Testing | High | 2 | 0.5 | 2028-09-03 | 2028-09-13 | 10 | Description 1
Content | Team | Kylie R | Project Charter Revisions | Reason 2 | In Progress | Medium | 4 | 1 | 2028-09-03 | 2028-09-07 | 4 | Description 2
Research | All | Pete S | Research | Reason 3 | Ready to Start | Low | 5 | 2 | 2028-09-07 | 2028-09-12 | 5 | Description 3
Task | Developer | Steve L | Projections | Reason 4 | Complete | Medium | 6 | 0.25 | 2028-09-09 | 2028-09-13 | 4 | Description 4
Update | Customer | Allen W | Stakeholders |  | Testing | Medium | 3 | 0.25 | 2028-09-16 | 2028-09-24 | 8
Update |  | Malik M | Guidelines |  | In Progress | High | 1 | 3 | 2028-09-16 | 2028-09-17 | 1
Feature |  | Malik M | Project Initiation |  | Complete | Medium | 1 | 1 | 2028-09-17 | 2028-09-21 | 4
Feature |  | Allen W | Scope and Goal Setting |  | Complete | Medium | 2 | 2 | 2028-09-22 | 2028-09-24 | 2
Research |  | Allen W | Budget |  | On Hold | High | 1 | 0.25 | 2028-09-25 | 2028-10-05 | 10
Research |  |  |  |  | Testing | High |  |  | 2028-09-25 | 2028-09-29 | 4
Research |  |  |  |  | Testing | High |  |  | 2028-09-24 | 2028-10-02 | 8
Research |  |  |  |  | Testing | High |  |  | 2028-10-02 | 2028-10-05 | 3
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
[7 empty] | 25 | 10.25 |  |  | 63
TASKS
CLICK HERE TO CREATE IN SMARTSHEET
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
AW
PS
MM

## Dropdown Keys
KEY DROPDOWNS - DO NOT DELETE
CATEGORY KEY | PRIORITY KEY | STATUS KEY
Research | High | In Progress
Story - Patient | Medium | Ready to Start
Story - Caregiver | Low | DONE
Task | Medium Low | On Hold
Update |  | Testing
Sprint 0 |  | Estimate
Sprint 1

## OLD ACS (hidden)
Everdose Product Acceptance Criteria
# | DESCRIPTION | PRIORITY | POINTS | HOURS | Acceptrance Criteria | Acceptrance Criteria | Acceptrance Criteria
08 | As a patient, | High | 5 | 24 | - The app should display a list of all the medications the patient has taken, along with the date and time of each dose. | - The app should provide a way for the patient to manually add medications to their history if necessary. | Patients can't set up medication schedules unless the medication details are updated.
| I want to be able to set up multiple medication schedules for different times of the day, |  |  |  | - The medication history should be easily accessible from the main menu of the app. | - The app should send reminders to the patient when it's time to take their medication, based on the medication history. | All data from schedules are stored in medication schedule database.
| So that I can keep track of all my medications and receive reminders when it's time to take my medication. |  |  |  | - The patient should be able to filter the medication history by date or medication name.
02 | As a patient, | High | 5 | 24 | - The app should display a list of all the medications the patient has taken, along with the date and time of each dose. | - The app should send reminders to the patient when it's time to take their medication, based on the medication history. | Only the patient and authorised carers can access the history.
| I want to be able to view my medication history in the app, |  |  |  | - The patient should be able to filter the medication history by date or medication name. | - The app should allow the patient to add notes or explanations. | Login must be required before viewing the history.
| So that I can see whether I've missed any doses. |  |  |  | - The app should highlight any missed doses in the medication history with visual (red text or warning icon) | - The app should send a notification to the patient and caregiver if an overdose is detected. | The patient should be able to change status (from missed dose to taken) after he/she took medications.
03 | As a patient, | High | 2 | 4 | - The app should Include overdose information within the medication history view. | - The patient should be able to filter the medication history by date or medication name. | Overdose status must not be changible for audit purpose.
| I want to be able to view my medication history in the app, |  |  |  | - The app should allow the patient to add notes or explanations. | - The app should calculate the total amount of medication the patient has taken for each medication. | the patient can see the timeline of medication history.
| So that I dont overdose |  |  |  | - The app should display a list of all the medications the patient has taken, along with the date and time of each dose. | - The app should display a warning message if the total amount of medication taken by the patient exceeds the prescribed dosage, by highlighting them with visual (red text or warning icon)
09 | As a patient, | High | 3 | 16 | - The app should allow the patient to set up reminders for each medication they take. | - The patient should be able to snooze or dismiss the reminders if necessary. | The patient must be registered and logged in to get notification from the app.
| I want to be able to receive reminders for when I need to take medications, |  |  |  | - The reminders should be customizable and allow the patient to set the frequency and time of day for each medication. | - The app should provide a way for the patient to mark the medication as taken or skipped from the reminder notification itself. | The patient should be able to change the ringtone.
| So that I don't forget to take them when I need them. |  |  |  | - The app should send reminders to the patient at the scheduled times.
20 | As a caregiver responsible for multiple patients, | High | 5 | 24 | - The app should allow the caregiver to add and manage medication schedules for multiple patients. | - The app should send reminders to the caregiver when it's time to provide medication to each patient. | The carer must be authorised and registered in the app.
| I want to be able to manage medication schedules for multiple patients within the app, |  |  |  | - The caregiver should be able to view a list of all the patients they are responsible for, along with their patient’s medication schedules. | - The caregiver should be able to mark the medication as given or missed for each patient.
| So that I can efficiently monitor and provide care for each patient. |  |  |  | - The caregiver should be able to filter the list of patients by name or medication name.
13 | As a caregiver, | High | 2 | 4 | - The app should allow patients to grant caregivers access to view their medication schedules and histories. | - The caregiver should be able to view the missed medication doses for each patient. | All changed data must be recorded and stored in medication schedules database.
| I want to receive notifications when the patient misses a medication dose, |  |  |  | - The app should send push notifications or other alerts to the caregiver if the patient misses a medication dose. | - The caregiver should be able to mark the missed medication as given or remind the patient to take the medication.
| So that I can remind them to take it. |  |  |  | - The notification should include the patient name, medication name, dosage, and scheduled time. | - The app should send a notification to the patient when the caregiver marks the missed medication as given.
21 | As a patient or caregiver, | Medium | 0 | 0
I want the Everydose Application to integrate with emergency contacts,
So that I can easily reach out for help in case of a medication-related emergency.
04 | As a patient, | Medium | 0 | 0
I want to be able to view my medication history in the app,
So that I can see whether I've been taking my medication on time.
05 | As a patient, | Medium | 0 | 0
I want to be able to take a picture of my medications before intake,
So that a carer could investigate my record if any medical issue happened.
07 | As a patient, | Medium | 0 | 0
I want to be able to update how many doses I've been prescripted,
So that I can check when the next prescription date is.
10 | As a patient, | Medium | 0 | 0
I want to be able to communicate with caregiver or in-charged nurse through the app in real-time,
So that I can ask for help or if I have any enquiries about the medication.
16 | As a caregiver, | Medium | 0 | 0
I want to be able to view the patient's medication list and dosages in the app,
So that I can make sure they're taking the right medication at the right time.
17 | As a caregiver, | Medium | 0 | 0
I want to be able to view the patient's medication intake history,
So that I can follow up whether the patient takes the right medications and have this information in case of emergencies.
01 | As a patient, | Low | 0 | 0
I want to be able to schedule my medication times in the app,
So that I can receive reminders when it's time to take my medication
06 | As a patient, | Low | 0 | 0
I want to be able to receive reminders when I need to refill my medication,
So that I don't run out.
11 | As a patient, | Low | 0 | 0
I want the app to display relevant information about each medication, such as side effects, interactions, and precautions.
So that I can understand the medications better and avoid potential mix-ups or misunderstandings.
12 | As a patient , | Low | 0 | 0
I want to be able to access my medication schedule and information offline,
So that I can continue managing my medications even without internet access.
14 | As a caregiver, | Low | 0 | 0
I want to receive notifications when the patient takes a medication dose,
So that I can keep updating their intake.
15 | As a caregiver, | Low | 0 | 0
I want to be able to add new medications to the patient's medication list in the app,
So that I can keep their medication schedule up to date.
18 | As a caregiver, | Low | 0 | 0
I want to be able to view the patient's medication intake photos taken,
So that I can make sure whether the patient takes the right medications.
19 | As a caregiver, | Low | 0 | 0
I want to be able to track the patient's medication adherence over time,
So that I can see if there are any patterns or issues that need to be addressed.
BACKLOG
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
X
XX
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0

## ARCHIVE (hidden)
ARCHIVE |  | Fill in the spreadsheet below with tasks that are ready for archiving.
CATEGORY | ROLE | ASSIGNED TO | ACTION | RATIONALE | STATUS | PRIORITY | POINTS | HOURS | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Feature | Team | Name | Action 1 | Reason 1 | In Progress | High | 0 | 0 | 2028-09-03 | 2028-09-13 | 10 | Description 1
Content | Team | Name | Action 2 | Reason 2 | In Progress | Medium | 0 | 0 | 2028-09-03 | 2028-09-07 | 4 | Description 2
Research | All | Name |  | Reason 3 | Testing | Low | 0 | 0 |  |  | 0 | Description 3
Task | Developer |  |  | Reason 4 | Testing | Medium | 0 | 0 |  |  | 0 | Description 4
Update | Customer |  |  |  | Testing | Medium | 0 | 0 |  |  | 0
Update |  |  |  |  | In Progress | High | 0 | 0 |  |  | 0
Feature |  |  |  |  | On Hold | Medium | 0 | 0 |  |  | 0
Feature |  |  |  |  | On Hold | Medium | 0 | 0 |  |  | 0
Research |  |  |  |  | On Hold | High | 0 | 0 |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
[7 empty] | 0 | 0 |  |  | 14

## Template Backlog (hidden)
BACKLOG |  | Fill in the spreadsheet below. Then, use the tools on the Kanban Template Tab of this document to copy and paste Kanban cards and personnel icons to the Backlog Kanban board below this table.
CATEGORY | ROLE | ASSIGNED TO | ACTION | RATIONALE | STATUS | PRIORITY | POINTS | HOURS | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Feature | Team | Name | Action 1 | Reason 1 | In Progress | High | 0 | 0 | 2028-09-03 | 2028-09-13 | 10 | Description 1
Content | Team | Name | Action 2 | Reason 2 | In Progress | Medium | 0 | 0 | 2028-09-03 | 2028-09-07 | 4 | Description 2
Research | All | Name |  | Reason 3 | Testing | Low | 0 | 0 |  |  | 0 | Description 3
Task | Developer |  |  | Reason 4 | Testing | Medium | 0 | 0 |  |  | 0 | Description 4
Update | Customer |  |  |  | Testing | Medium | 0 | 0 |  |  | 0
Update |  |  |  |  | In Progress | High | 0 | 0 |  |  | 0
Feature |  |  |  |  | On Hold | Medium | 0 | 0 |  |  | 0
Feature |  |  |  |  | On Hold | Medium | 0 | 0 |  |  | 0
Research |  |  |  |  | On Hold | High | 0 | 0 |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
Research |  |  |  |  | Testing | High |  |  |  |  | 0
[7 empty] | 0 | 0 |  |  | 14
BACKLOG
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
XX
XX
XX